## Summary
LOOK-AHEAD FOR DESIGN PACKAGES
PROJECT | TOWER | In 30 days | In 60 days
JB NAGAR | SOCIETY | Landscape works | -
Compound wall/ Internal Road
MEP works (Soc B,C,D)
| SALE - DEF | Aluminium Windows (BOQ) | -
Fins/GRC, Glass railing (BOQ)
Lift lobby,
Tremix/ VDF
Infra works, Landscape,
Plumbing Pump, HVAC
KRIPANAGAR | PLOT-A | Aluminium Windows | Clubhouse, Entrance lobby
Fins/GRC, Glass railing
| PLOT-B | Aluminium Windows (BOQ) | -
Fins/GRC, Glass railing (Drawing & BOQ)
Clubhouse, Entrance lobby,
Lift lobby,
Tremix/ VDF
Infra works, Landscape
KALINA-1 | REHAB 1 | Aluminium formwork | CP & sanitary, Finishing package
| COMMERCIAL | Passive anchoring | Finishing package
NISCHAY | PTC | - | Aluminium formwork
| HOSTEL | MEP works | -
DESIGN PACKAGES - CRITICAL
PROJECT | TOWER | CONSULTANT | TARGET
KRIPA NAGAR | PLOT-B | Aluminium windows, GRC/ Fins, Glass railing | 15-May 10-Aug
JB NAGAR | SALE DEF | Aluminium windows, GRC/ Fins, Glass railing | 15-May 10-Aug
| SOC BCD | MEP works | 15-Jul 30-Aug
NISCHAY | HOSTEL | MEP works | 30-Jun 30-Aug
CONSULTANT ONBOARDING - CRITICAL
PROJECT | TOWER | CONSULTANT
KALINA-2 | COMMERCIAL, REHAB | MEP Consultant (Work order not given)
KALINA-1 | COMMERCIAL | Facade Consultant
| COMMERCIAL, REHAB, SOC | STP Consultant/ Vendor
VANRAI |  | Geotech Consultant
KANHERI |  | Traffic Consultant

## Projects
CHANDAK TENDER DESIGN TRACKER
CONSULTANT | WORK PACKAGES | JB NAGAR |  | KRIPANAGAR |  | CHEMBUR |  | KALINA-1 |  |  | KALINA-2 |  | RBD TOWER-E | NISCHAY |  | MERU |  | VANRAI |  | KANHERI |  |  |  | WORLI
|  | SOCIETY | SALE - DEF | PLOT-A | PLOT-B | SALE 1,2,7,8 | REHAB-4 | REHAB 1 | SOCIETY | COMMERCIAL | REHAB | COMMERCIAL | SALE | PTC | HOSTEL | REHAB | COMMERCIAL | SOCIETY | SALE | SOCIETY | SALE | REHAB | COMMERCIAL | SRA | SALE
Traffic Consultant | Traffic analysis | Received | Received | Received | Received | Received | Received | Received | Received | Received | In progress | In progress | Onboard | NA | NA | Traffic analysis received | Traffic analysis received | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Flood risk consultant | Flood analysis | Received | Received | Received | Received | NA | NA | NA | NA | NA | In progress | In progress | NA | NA | NA | Not Onboard | Not Onboard | NA | NA | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Green Building Consultant | IGBC compliance | In progress | In progress | In progress | In progress | In progress | NA | In progress | In progress | In progress | In progress | In progress | NA | NA | NA | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Environment Consultant | MOEF compliance | Received | Received | Received | Received | Received | Received | Received | Received | Received | Onboard, compliance pending | Onboard, compliance pending | Onboard | Received | Received | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard
HRC consultant (>180m height) |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Not Onboard | Not Onboard
Wind tunnel Consultant (>180m height) |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Not Onboard | Not Onboard
Geotech peer-review consultant (>120m height) |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Not Onboard | Not Onboard | Not Onboard | NA | NA | NA | NA | Not Onboard | Not Onboard
Structural peer-review consultant (>120m height) |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Not Onboard | Not Onboard | Not Onboard | NA | NA | NA | NA | Not Onboard | Not Onboard
Civil Works
Soil Investigation | Bore log & Soil Investigation report | Received | Received | Received | Received | Received | Received | Received | Received | Received | Onboard, report pending | Onboard, report pending | Onboard, borehole details pending | Received | Received | Received | Received | Onboard, report pending | Onboard, report pending | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Geotechnical consultant | Shore Piling Works | Received | Received | Received | Received | NA | Received | Received | Received | Received | Onboard | Onboard |  | Received | Received | Not onboard | Not onboard | Not Onboard | Not Onboard
| Foundation Rock Anchoring | Received | Received | Received | Received | Received | Received | 2026-08-25 |  |  | Onboard | Onboard |  | Received | Received | Not onboard | Not onboard | Not Onboard | Not Onboard
| Inclined Rock Anchoring | Received | Received | Received | Received | Received | Received | Received | Received | Received | Onboard | Onboard |  | Received | Received | Not onboard | Not onboard | Not Onboard | Not Onboard
Structural Consultant | Excavation work | Received | Received | Received | Received | Received | Received | Received | Received | Received | Onboard | Onboard | Pending | Received | Received | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
| Core and Shell works | Received | Received | Received | Received | Received | Received | Received | Received | Received |  |  | Received | Received | Received
| Blockwork | Received | Received | Received | Received | Received | Received | 2026-09-15 | 2026-09-15 | 2026-09-15 |  |  | Received | Received | Received
| Expansion joint | NA | NA | NA | NA | Received | Received | 2026-09-15 | 2026-09-15 | 2026-09-15 |  |  | Pending | NA | NA
| Mivan | Received | Received | Received | Received | Received | Received | 2026-09-15 | 2026-11-30 | 2026-10-30 |  |  | Pending | 2026-09-30 | Received
| PT works | Received | Received | Received | Received | Received | Received | NA | NA | 2026-10-30 |  |  | Pending | NA | NA
MEP
MEP Consultant | Plumbing Works | Received for Soc A, 30-Aug for B,C,D | Received | Pending | Received | Received | Received | MEP Consultant Onboard, SD stage | MEP Consultant Onboard, SD stage | MEP Consultant Onboard, CD stage | MEP Consultant Onboard, work not started, WO not given | MEP Consultant Onboard, work not started, WO not given | MEP Consultant Onboard, SD stage | Pending | 2026-08-30 | MEP Consultant Onboard, SD stage | MEP Consultant Onboard, SD stage | MEP Consultant Onboard, SD stage | MEP Consultant Onboard, SD stage | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
| Plumbing Pump | Received for Soc A, 30-Aug for B,C,D | Received | Pending | Received, scheme will be revised as fire tank proposed at terrace | Received | Received | [6 empty] | Pending | 2026-08-30
| Electrical works | Received for Soc A, 30-Aug for B,C,D | Received | Pending | Received | Received | Received | [6 empty] | Pending | 2026-08-30
| Electrical panels | Received for Soc A, 30-Aug for B,C,D | Received | Pending | Received | Received | Received | [6 empty] | Pending | 2026-08-30
| Fire fighting | Received | Received | Pending | Received | Received | Received | [6 empty] | Pending | 2026-08-30
| Fire Alarm & Public Address | Received for Soc A, 30-Aug for B,C,D | Received | Pending | Received | Received | Received | [6 empty] | Pending | 2026-08-30
| Fire Pumps | Received for Soc A, 30-Aug for B,C,D | Received | Pending | Received | Received | Received | [6 empty] | Pending | 2026-08-30
| Mechanical ventilation and HVAC | Received for Soc A, 10-Sep for B,C,D | 2026-09-15 | Pending | Received | Received | Received | [6 empty] | Pending | 2026-08-30
| Lighting Protection system (LPS) | Received | Received | Received | Received | Received | Received | [6 empty] | Received | Received
| Electrical Infra works | 2026-10-30 | 2026-10-30 | Pending | 2026-10-30 | Pending | Pending | [6 empty] | Pending | Pending
| Aviation lights | 2026-10-30 | 2026-10-30 | Pending | 2026-10-30 | Received | Received | [6 empty] | Pending | Pending
| Solar Panel | 2026-10-30 | 2026-10-30 | Pending | 2026-10-30 | Received | Received | [6 empty] | Pending | Pending
| BMS/CCTV/Security Control | 2026-10-30 | 2026-10-30 | Pending | 2026-10-30 | Received | Received | [6 empty] | Pending | Pending
| DG Set | 2026-10-30 | 2026-10-30 | Pending | 2026-10-30 | Received | Received | [6 empty] | Pending | 2026-08-30
| SWD works | 2026-10-30 | 2026-10-30 | Pending | 2026-10-30 | Pending | Pending | [6 empty] | Pending | Pending
| Organic waste composter | 2026-10-30 | 2026-10-30 | Pending | 2026-10-30 | Received | Received | [6 empty] | Pending | Pending
Vertical Transport Consultant | Passenger lift and escalator | Received | Received | Pending | Received | Received | Received | NA | NA | Onboard, 1st cut report received | Not Onboard | Not Onboard | Not Onboard | NA | NA | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
| Mechanical Car park | Pending | Pending | Pending | Pending | Received | Received
STP Consultant | STP | Received | Received | Received | Received | Received | Received | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard in 2 months | Not Onboard | Received | Received | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
IT Consultant | IT | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Lighting Consultant | Façade/Interior Lights | NA | NA | NA | NA | NA | NA | NA | NA | Onboard | NA | Not Onboard | NA | NA | NA | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Swimming pool/ Water body |  | NA | Not Onboard | Not Onboard | Not Onboard | Onboard | NA | NA | NA | NA | NA | NA | Not Onboard | NA | NA | NA | NA | NA | Not Onboard | NA | Not Onboard | NA | NA | NA | Not Onboard
Finishing
Architect/SRA Architect | Architectural drawings | Received | Received | Received | Received | Received | Received | Received | Received | Received | Onboard | Onboard | Received | Received | Received | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard
| Door frame and shutter | Received | Received | 2026-11-30 | Received | Received | Received | 2026-09-30 | 2026-11-30 | 2026-10-15 |  |  | Pending | Pending | Pending
| Flooring/Tiling /Dado | Received | Received | 2026-11-30 | Received T1,2, 8A, 8B T6,7 - 25-Aug | Received | Received | 2026-09-30 | 2026-11-30 | 2026-10-15 |  |  |  | Pending | Pending
| Internal painting | Received | 2026-08-30 | 2026-11-30 | Received T1,2, 8A, 8B T6,7 - 25-Aug | Received | Received | 2026-09-30 | 2026-11-30 | 2026-10-15 |  |  |  | Pending | Pending
| Railings MS/SS (Window/Staircase) | Received | Received | 2026-11-30 | Received | Received | Pending | 2026-09-30 | 2026-11-30 | 2026-10-15 |  |  |  | Pending | Pending
| CP and sanitary material | Received | Received | Received | Received | Received | Received | 2026-09-30 | 2026-11-30 | 2026-10-15 |  |  |  | Pending | Pending
| Parking & Ramp - Tremix/VDF | 2026-08-30 | 2026-08-30 | 2026-11-30 | 2026-08-30 | Received | Received | 2026-09-30 | 2026-11-30 | 2026-10-15 |  |  |  | NA | NA
| External painting | Received | Received | 2026-11-30 | 2026-08-30 | Received | Pending | 2026-09-30 | 2026-11-30 | 2026-10-15 |  |  |  | Pending | Pending
| Lift lobby | Received | 2026-08-30 | 2026-11-30 | 2026-08-30 | Received | Pending | 2026-09-30 | 2026-11-30 | 2026-10-15 |  |  |  | Pending | Pending
Interior consultant | Clubhouse, Amenities | Received | Received | 2026-10-15 | 2026-08-15 | Pending | NA | NA | NA | Onboard | NA | Not Onboard | Not Onboard | NA | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
| Entrance lobby | Received | Received | 2026-10-15 | 2026-08-15 | Pending
| Lights | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Pending
| Loose Furniture | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Pending
| Artefacts | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Pending
| Experience Centre | NA | Received | Received | Received | Received |  |  |  | NA |  | NA |  |  | NA
Façade consultant | Aluminium windows | Received | Received for DEF | Received | Received | Received | Pending | Not Onboard | Not Onboard | Not Onboard, Immediately required | Not Onboard | Not Onboard, required in 3-4 months | Not Onboard | NA | NA | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
| Fins/GRC | NA | Received for DEF | Received | Received | Pending | Pending
| Glass Railing | NA | Received for DEF | Received | Received | Received | NA
Landscape consultant | Landscape | 2026-08-30 | 2026-08-30 | 2026-11-30 | 2026-08-30 | Received | NA | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Onboard | NA | NA | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
| Compound wall/Internal Road | 2026-08-30 | 2026-08-30 | 2026-11-30 | 2026-08-30 | Received | NA
Kitchen and BOH consultant |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Onboard, tender pending | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Signages Consultant | Signages | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Pending | Pending | NA | NA | Not Onboard | NA | Not Onboard | Not Onboard | Pending | Pending | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Legend
Drawings received
In progress - On track
Delayed
Not Applicable
Formulas:
COMMERCIAL = [COMMERCIAL, row above]
Note on M15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technogem
Note on H34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: After architect/landscape input - 1.5 months

## Sheet1 (hidden)
Stage | Consultant | Key Deliverables
1. Feasibility | Surveyor | Topographical survey, boundary survey, site contours
| Liaison Architect | Approval roadmap, DCPR analysis, statutory applicability matrix
| Revenue & Valuation Consultant | FSI potential, development feasibility, revenue assessment
| CRZ / Railway / Special NOC Consultants (if applicable) | Constraint analysis and NOC requirements
| Traffic Consultant (if applicable) | Preliminary traffic impact assessment
| Flood Risk Consultant (if applicable) | Flood-level assessment, basement feasibility
2. Concept Design Freeze (20-30%) | Architect | Concept plans, area statements, parking layouts, massing studies
| Green Building Consultant | Sustainability strategy, IGBC targets
| Environment Consultant | Environmental compliance strategy
| Traffic Consultant | Parking demand and circulation strategy
| Flood Consultant | Finished floor level recommendations
3. Design Basis Freeze (30-40%) | Geotechnical Consultant | Soil investigation report, foundation recommendations
| Structural Consultant | Structural Design Basis Report (DBR), column grid, slab system
| MEP Consultant | MEP Design Basis Report, utilities strategy, plant room sizing
| Vertical Transport Consultant | Lift traffic analysis, lift configuration
| STP Consultant | Sewage load calculations, STP sizing
4. Schematic Design Freeze (40-60%) | Structural Consultant | Foundation scheme, RCC framing concept, transfer structures
| MEP Consultant | Shaft layouts, coordinated services strategy, load calculations
| Façade Consultant | Façade performance strategy, glazing concept
| Vertical Transport Consultant | Final lift sizing and shaft requirements
| Landscape Consultant | Podium/open space strategy
5. Detailed Design (60-80%) | Structural Consultant | Detailed structural drawings
| MEP Consultant | Detailed MEP layouts and schematics
| Façade Consultant | Façade drawings and specifications
| IT Consultant | IT, CCTV, BMS, security system design
| Swimming Pool Consultant (if applicable) | Pool hydraulic and MEP design
| Lighting Consultant | Common area and façade lighting design
6. Tender Design & Procurement Readiness (80-100%) | Structural Consultant | Excavation, RCC, Mivan, PT tender drawings, BOQ
| MEP Consultant | Plumbing, firefighting, HVAC, electrical tender packages
| Façade Consultant | Façade BOQ, specifications, tender package
| Vertical Transport Consultant | Lift procurement package
| Landscape Consultant | Landscape BOQ and tender package
| Interior Consultant | Amenity, clubhouse, lobby tender package
| Signage Consultant | Signage package and specifications
| Kitchen & BOH Consultant (if applicable) | Kitchen equipment specifications and BOQ
7. Pre-Construction / GFC | Architect | GFC architectural drawings
| Structural Consultant | GFC structural drawings
| MEP Consultant | Coordinated GFC MEP drawings
| Façade Consultant | IFC/GFC façade details
| Interior Consultant | Approved material schedules and GFC interiors
8. Construction Support | TPQA Consultant | QA/QC framework, audit reports
| PMC Consultant | Monitoring and progress control
| Site Supervisor | Compliance certification
| Fire Consultant | Compliance review and approvals support

## Liaisoning
CHANDAK CONSULTANTS TRACKER - LIAISONING
CONSULTANT | WORK PACKAGES | JB NAGAR |  | KRIPANAGAR |  | CHEMBUR |  | NISCHAY |  | KALINA-1 |  |  | KALINA-2 |  | RBD TOWER-E | MERU |  | VANRAI |  | KANHERI |  |  |  | WORLI
|  | SOCIETY | SALE | PLOT-A | PLOT-B | SALE 1,2,7,8 | REHAB-4 | PTC | HOSTEL | REHAB | SOCIETY | COMMERCIAL | REHAB | COMMERCIAL | SALE | REHAB | COMMERCIAL | SOCIETY | SALE | SOCIETY | SALE | REHAB | COMMERCIAL | SRA | SALE
Liaisoning Architect | Building Plan approval | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard
RERA consultant | RERA compliance | Onboard | Onboard | Onboard | Onboard | Onboard | NA | NA | NA | NA | NA | Onboard | NA | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | NA | Onboard | NA | Onboard | Not Onboard | Not Onboard
Plumbers |  | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Fixed consultant
TPQA Consultant | ONLY CERTIFICATE | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Fixed consultant
Site Supervisor | ONLY CERTIFICATE | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Fixed consultant
PMC Consultant | ONLY CERTIFICATE | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Fixed consultant
Horticulturist | Tree NOC | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Surveyor |  | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Fixed consultant
Civil Aviation |  | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Borewell Consultant |  | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Road consultant |  | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Railway NOC Consultant |  | Onboard | Onboard | Onboard | Onboard | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
CRZ Consultant |  | Onboard | Onboard | Onboard | Onboard | NA | NA | NA | NA | NA | NA | NA | Not Onboard | Not Onboard | NA | NA | NA | Onboard | Onboard | NA | NA | NA | NA | Not Onboard | Not Onboard
Fire Consultant |  | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Revenue & Valuation Consultant |  | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard
Electric Consultant |  | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
HT line |  | NA | NA | NA | NA | Onboard | Onboard | NA | NA | NA | NA | NA | Onboard | Onboard | NA | NA | NA | Onboard | Onboard | NA | NA | NA | NA | Not Onboard | Not Onboard
Traffic Consultant | Traffic analysis | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | NA | NA | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Flood risk consultant | Flood analysis | Onboard | Onboard | Onboard | Onboard | NA | NA | NA | NA | NA | NA | NA | Onboard | Onboard | NA | Not Onboard | Not Onboard | NA | NA | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Green Building Consultant | IGBC compliance | Onboard | Onboard | Onboard | Onboard | Onboard | NA | NA | NA | Onboard | Onboard | Onboard | Onboard | Onboard | NA | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard | Not Onboard
Environment Consultant | MOEF compliance | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard, compliance pending | Onboard, compliance pending | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Onboard | Not Onboard | Not Onboard
HRC consultant (>180m height) |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Not Onboard | Not Onboard
Wind tunnel Consultant (>180m height) |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Not Onboard | Not Onboard
Geotech peer-review consultant (>120m height) |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Not Onboard | Not Onboard | Not Onboard | NA | NA | NA | NA | Not Onboard | Not Onboard
Structural peer-review consultant (>120m height) |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Not Onboard | Not Onboard | Not Onboard | NA | NA | NA | NA | Not Onboard | Not Onboard
Legend
Onboard
Not Onboard |  | Not Onboard
Not Applicable